## PROJECT DETAILS
PROJECT NAME
Project Members
DATE

## WEEK 1
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Raghad | What did you you do yesterday? | N/A | Attended project introduction and discussed frontend responsibilities. | Collected design ideas for homepage layout. | Created draft wireframes and shared them with team. | Finished the homepage wireframe with small adjustments.
| What are doing today? | Attending the kickoff meeting and understanding the system requirements. | Reviewing similar event platforms for design inspiration. | Drafting simple sketches for homepage structure. | Adjusting wireframe based on feedback from Shahad and Rania. | Reviewing design alignment with Shahad before starting actual coding next week.
| Is there anything blocking you? | None | None | None | None | None
Lamyaa | What did you you do yesterday? | N/A | Understood backend responsibilities and project goals | Reviewed potential frameworks for the system backend. | Designed initial ER diagram for the database. | Finalized the database structure and ER diagram.
| What are doing today? | Joined the kickoff meeting and listened to backend expectations. | Researching backend tools and possible database structures. | Reviewed potential frameworks for the system backend. | Finalizing database tables and sharing with team for feedback. | Reviewing backend plan and confirming data requirements with Rania.
| Is there anything blocking you? | None | None | None | None | None
Rania | What did you you do yesterday? | N/A | Introduced the product concept and team responsibilities. | Completed draft of the Vision Statement. | Finalized the Product Backlog structure. | Reviewed backlog priorities with the team.
| What are doing today? | Presented project vision and explained goals to the team. | Drafting Product Vision and identifying stakeholders. | Start outlining the Product Backlog (high-level items). | Review backlog priorities and confirm with Scrum Master. | Preparing short summary for Sprint 1 goals.
| Is there anything blocking you? | None | None | None | None | None
Shahad | What did you you do yesterday? | N/A | Understood the project goals and user needs. | Created moodboard and initial color scheme ideas. | Designed draft user flow and discussed with the team. | Completed user flow and low-fidelity wireframes.
| What are doing today? | Joined the kickoff meeting and listened to product goals. | Brainstorming color palettes and style direction for the app. | Sketching basic user flow (from browsing to booking). | Start preparing low-fidelity wireframes with Raghad. | Organizing all design files and feedback to be ready for Sprint 1.
| Is there anything blocking you? | None | None | None | None | None
Layan | What did you you do yesterday? | N/A | Organized first team meeting and assigned initial duties. | Finalized sprint goals with Rania. | Completed Scrum board setup and reviewed progress. | Reviewed progress of all team members.
| What are doing today? | Led the kickoff meeting and introduced Scrum roles. | Preparing sprint planning outline for next meeting. | Creating the Scrum board and explaining workflow to the team. | Checking that everyone is aligned before starting Sprint 1 next week. | Conducting short team reflection meeting and finalizing next week’s Sprint plan.
| Is there anything blocking you? | None | None | None | None | None

## WEEK 2
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Raghad the UI designer | What did you you do yesterday? | ___ | Design the admin dashboard interface with clear data respresntaion. | add delete and add ticket events for users | add visualzation, consistent colors,icons and layouts | Test user interfaces and fix issuses
| What are doing today? | Design the admin dashboard interface with clear data respresntaion. | add delete and add ticket events for users | add visualzation, consistent colors,icons and layouts | Test user interfaces and fix issuses | Prepare mochups.
| Is there anything blocking you? | None | None | None | None | None
Lamyaa the scrum master | What did you you do yesterday? | ___ | Start sprint planning and dayly scrum cordnations | work on admin dashboard and login authintcation | add aprrove and reject buttons in admin page | test backend and database
| What are doing today? | Start sprint planning and dayly scrum cordnations | work on admin dashboard and login authintcation | add aprrove and reject buttons in admin page | test backend and database | wirte sprint retrospective and report the progress.
| Is there anything blocking you? | None | None | integration daleys | None | None
layan the frontend dev | What did you you do yesterday? | ___ | start implemting registration and login | Connected authentication between frontend and backend | implement event browsing with filters | test all frontend implementation
| What are doing today? | start implemting registration and login | Connected authentication between frontend and backend | implement event browsing with filters | test all frontend implementation | test all frontend implementation and prepare a demo.
| Is there anything blocking you? | None | None | wait for connection to backend database. | None | None
Shahad the product owner | What did you you do yesterday? | ___ | Design event creation form. | link event form to database | add admin approve and rejection flows. | test issue tracking and live chating
| What are doing today? | Design event creation form. | link event form to database | add admin approve and rejection flows. | test issue tracking and live chating | Present sprint review to all members.
| Is there anything blocking you? | None | None | None | None | None
Rania the backend dev | What did you you do yesterday? | ___ | create and build database tables | write signup and booking logic | integrate frontend with backend | test all functions and fix issuses
| What are doing today? | create and build database tables | write signup and booking logic | integrate frontend with backend | test all functions and fix issuses | prepare API document.
| Is there anything blocking you? | None | None | None | None | None

## WEEK 3
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Raghad | What did you you do yesterday? | I have finished designing the dashboard UI for managing users and events. | Completed create and delete operations. | Finished edit/update functions and tested them. | Added data consistency checks and monitoring tools. | Completed dashboard integration with backend.
| What are doing today? | Implement create and delete operations for admin dashboard . | Add edit and update functionality for data management. | Implement data validation for events forms. | Run full dashboard testing. | Finalize documentation and backup database.
| Is there anything blocking you? | None | No blockers. | None | No blockers. | None
Lamyaa | What did you you do yesterday? | Finalized login and authentication system setup. | Implemented approve/reject logic in the Admin Event Review page for event workflow. | Completed alert integration with admin approval. | Fixed access control bugs in dashboard. | Completed final testing and deployed admin features.
| What are doing today? | Add admin approval functions for event publishing. | Integrate a function for Send alert messages after admin decisions. | Begin system testing for role-based access. | Prepare documentation for authentication flow. | Review final report for sprint completion.
| Is there anything blocking you? | No blockers | Waiting on Shahad’s notification module. | No blockers. | No blockers. | None
Rania | What did you you do yesterday? | Finalized the design layout for the “Event Browsing” page. | Implemented filtering logic for events by category. | Completed all filter functionalities and tested UI responsiveness. | Linked event data to frontend successfully. | Completed front-end testing and fixed minor layout bugs.
| What are doing today? | Start integrating the filter options (category/date/location). | Add date and location filters with dynamic updates. | Connect the page with live event data from database. | Work on visual refinements and loading indicators. | Prepare code for final merge to main branch.
| Is there anything blocking you? | No blockers. | Need backend endpoint confirmation. | Waiting for database access data. | No blockers. | No blockers.
Shahad | What did you you do yesterday? | Designed “Live Chat ” page layout. | Added quick-reply and auto-response templates. | Built backend logic for email/SMS notifications. | Fixed API issue and completed notification tests. | Completed feature integration successfully.
| What are doing today? | Implement reply feature and quick-reply templates. | Work on notification system for event updates. | Test notification delivery for event changes. | Integrate settings for enabling/disabling notifications. | Assist Lamyaa in testing admin alerts.
| Is there anything blocking you? | None. | No blockers. | Delay in email API verification. | None. | No blockers.
Layan | What did you you do yesterday? | Set up backend routes for signup and login functionalities. | Finished event booking logic with database connection. | Implemented attendee syncing with event data. | Completed attendance analytics APIs. | Deployed backend updates to testing environment.
| What are doing today? | Implement event booking logic and confirmation messages. | Develop attendee management backend functions. | Begin coding the analytics backend for attendance trends. | Optimize database queries for faster load times. | Conduct integration testing with frontend team.
| Is there anything blocking you? | No blockers. | Need database schema review from Raghad. | None so far. | No blockers. | None.

## WEEK 4
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Raghad the UI designer | What did you you do yesterday? | ___ | hekp in designing forget password form | review event logic in app. | help in creating edit event form | help in event form validation
| What are doing today? | hekp in designing forget password form | review event logic in app. | help in creating edit event form | help in event form validation | Develop backend logic to update the event in the database.
| Is there anything blocking you? | None | None | None | None | None
Lamyaa the scrum master | What did you you do yesterday? | ___ | Start sprint planning and dayly scrum cordnations | help in designing forget password form | Implement backend logic to generate a secure reset token and store it in the database. | continue Implementing backend logic.
| What are doing today? | Start sprint planning and dayly scrum cordnations | help in designing forget password form | Implement backend logic to generate a secure reset token and store it in the database. | continue Implementing backend logic. | work on Send password reset email/message function containing the secure reset link.
| Is there anything blocking you? | None | None | None | None | None
Rania the backend dev | What did you you do yesterday? | ___ | "event button" analysis and planing | implement "event button" | create edit event form | implement validation for (name, description, date, time, price, capacity, category, venue)
| What are doing today? | "event button" analysis and planing | implement "event button" | create edit event form | implement validation for (name, description, date, time, price, capacity, category, venue) | add recent progress in documet
| Is there anything blocking you? | None | None | None | None | None
Shahad the product owner | What did you you do yesterday? | ___ | integrating Instagram section to homepage UI | integration testing | fixing errors and dfects | final integration testing
| What are doing today? | integrating Instagram section to homepage UI | integration testing | fixing errors and dfects | final integration testing | add recent progress in documet
| Is there anything blocking you? | None | None | None | None | None
Layan the frontend | What did you you do yesterday? | ___ | Design “Forgot Password” form. | implement input validation for email. | Insert clickable Instagram link with brand style | Ensure Instagram link opens externally and works on all devices
| What are doing today? | Design “Forgot Password” form. | implement input validation for email. | Insert clickable Instagram link with brand style | Ensure Instagram link opens externally and works on all devices | add recent progress in documet
| Is there anything blocking you? | None | None | None | None | None

## WEEK 5
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Raghad | What did you you do yesterday? | ___ | continue Developing backend logic to update the event in the database. | design app logo. | continue designing app logo | halp in validating token function
| What are doing today? | continue Developing backend logic to update the event in the database. | design app logo. | continue designing app logo | halp in validating token function | Develop backend logic to delete event safely without breaking bookings/tickets.
| Is there anything blocking you? | None | None | None | None | None
Lamyaa | What did you you do yesterday? | ___ | work on Send password reset email/message function containing the secure reset link. | be avalibale for other members | help in delete event button funtion | halp in validating token function
| What are doing today? | work on Send password reset email/message function containing the secure reset link. | be avalibale for other members | help in delete event button funtion | halp in validating token function | add prgress in a document.
| Is there anything blocking you? | None | None | None | None | None
Rania | What did you you do yesterday? | ___ | test database data concictancy | add “Delete Event” button to allow organizer to remove an event. | continue working on “Delete Event” button to allow organizer to remove an event. | Implement confirmation prompt before deleting an event.
| What are doing today? | test database data concictancy | add “Delete Event” button to allow organizer to remove an event. | continue working on “Delete Event” button to allow organizer to remove an event. | Implement confirmation prompt before deleting an event. | add prgress in a document.
| Is there anything blocking you? | None | None | None | None | None
Shahad | What did you you do yesterday? | ___ | review priortized product backlog | check other member prgress | Validate token, update password in database, and show success confirmation. | continue to Validate token, update password in database, and show success confirmation.
| What are doing today? | review priortized product backlog | check other member prgress | Validate token, update password in database, and show success confirmation. | continue to Validate token, update password in database, and show success confirmation. | add prgress in a document.
| Is there anything blocking you? | None | None | None | None | None
Layan | What did you you do yesterday? | ___ | simplfy frontend code | Create “Reset Password” page to enter a new password using the token. | test reset password | fix errors and defects
| What are doing today? | simplfy frontend code | Create “Reset Password” page to enter a new password using the token. | test reset password | fix errors and defects | add prgress in a document.
| Is there anything blocking you? | None | None | None | None | None

## WEEK 6
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Raghad | What did you you do yesterday? | ___ | Develop backend logic to delete event safely without breaking bookings/tickets. | continue Developing backend logic to delete event safely without breaking bookings/tickets. | test deletion backend logic | Test user interfaces and fix issuses
| What are doing today? | Develop backend logic to delete event safely without breaking bookings/tickets. | continue Developing backend logic to delete event safely without breaking bookings/tickets. | test deletion backend logic | Test user interfaces and fix issuses | Prepare document.
| Is there anything blocking you? | None | None | None | None | None
Lamyaa | What did you you do yesterday? | ___ | check each member's prgress | make sure we acichived sprint goal | make sure we achived the difinition of done checklist | prepare sprint review document
| What are doing today? | check each member's prgress | make sure we acichived sprint goal | make sure we achived the difinition of done checklist | prepare sprint review document | prepare sprint retrospictive
| Is there anything blocking you? | None | None | None | None | None
Rania | What did you you do yesterday? | ___ | simplfy backend code | review database tables | integrate with frontend | test all APIs
| What are doing today? | simplfy backend code | review database tables | integrate with frontend | test all APIs | add prgress in a document.
| Is there anything blocking you? | None | None | need frontend data | None | None
Shahad | What did you you do yesterday? | ___ | review sprint backlog and product backlog | give feedback to stackholders | check member's progress | test final product
| What are doing today? | review sprint backlog and product backlog | give feedback to stackholders | check member's progress | test final product | check progress by document from all members
| Is there anything blocking you? | None | None | None | None | None
Layan | What did you you do yesterday? | ___ | add more icones to interfaces | test icons | integrate with backend | test all functions and fix issuses
| What are doing today? | add more icones to interfaces | test icons | integrate with backend | test all functions and fix issuses | add prgress in a document.
| Is there anything blocking you? | None | None | need backend data | None | None

## WEEK 7
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?