## Phase 1
SPRINT BACKLOG
CURRENT DATE | SPRINT START DATE | TOTAL ASSIGNED HOURS |  | HOURS USED |  | HOURS REMAINING
2025-10-19 | 2025-12-10 | 86 |  | 36 |  | 5
SPRINT GOAL | Deliver the core event management functionalities; including event browsing, creation, booking, and user managemen. To ensure a complete and functional MVP for the event platform.
SPRINT TRACKING |  |  |  |  | 2025-12-10 | 10/13/2025 | 10/14/2025 | 10/15/2025 | 10/16/2025 | 10/17/2025 | 10/18/2025 | 10/19/2025 | 10/20/2025 | 10/21/2025 | 10/22/2025 | 10/23/2025 | 10/24/2025 | 2025-12-10
User Stories and Tasks | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
User Story 1: As an event enthusiast I want to browse and search for events by category, date, or location so that I can easily find events that match my interests
Task 1.1 Design the event browsing interface (filters by category/date/location). | Rania Farhan | 7 | 7 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2 Connect browsing feature to the event database | Rania Farhan | 7 | 6 | 1 | 0 | 0 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
User Story 2: As an Event Organizer I want to create and publish my events on the platform so that I can reach more people and promote my event. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.1: Design “Create Event” form UI (title, date, description, image, capacity) | Shahad Alotaibi | 7 | 5 | 2 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.2: Implement backend logic for event creation and saving to database | Shahad Alotaibi | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.3: Enable event publishing & admin approval workflow | Shahad Alotaibi | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 3: As a Event Enthusiast l want to Book event tickets online so that I can save time and avoid waiting in lines |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 3.1 Design ticket booking UI with event details and seat options | Rania Farhan | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0
Task 3.2 Send confirmation email or message after successful booking | Layan Ahmad | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4
User Story 4: As a Event Enthusiast l want to Discover different events based on my interests so that I can attend events that match what I enjoy |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 4.1 Develop search and filter functions by category and location | Layan Ahmad | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0
Task 4.2 Implement recommendation system based on user preferences | Layan Ahmad | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 0
User Story 5: As an Admin, I want to manage users, permissions, and event data so that I can ensure the system is running smoothly and securely. |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 5.1 Design admin dashboard for managing users, permissions, and event data. | Raghad Alsemaih | 6 | 6 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 5.2 Implement management operations (create data,delete data, edit data). | Raghad Alsemaih | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Task 5.3 Test and maintain admin functions. | Raghad Alsemaih | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
Task 5.4 Monitor data consistency and accuracy. | Raghad Alsemaih | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
User Story 6: As an Event Organizer, I want to manage attendees and view booking analytics so that I can monitor event performance and attendance trends.
Task 6.1: Design attendee management interface (view, edit, remove attendee details) | Lamyaa Alotaibi | 5 | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 6.2 Implement backend logic for attendee data & syncing with event database | Lamyaa Alotaibi | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task 6.3 Develop analytics dashboard for attendance trends & booking stats | Lamyaa Alotaibi | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 86 | 36 | 5
Add More Tasks and User Stories if You Need to

## Phase 2
14-DAY SPRINT BACKLOG
10/19/25 | 2025-10-12 | 205 |  | 55 |  | 8
SPRINT GOAL | Deliver core event management functionalities including user registration, event browsing, event creation, event booking, event approval, and issue tracking.
SPRINT TRACKING |  |  |  |  | 2025-10-12 | 10/13/2025 | 10/14/2025 | 10/15/2025 | 10/16/2025 | 10/17/2025 | 10/18/2025 | 10/19/2025 | 10/20/2025 | 10/21/2025 | 10/22/2025 | 10/23/2025 | 10/24/2025 | 2025-10-12
User Stories and Tasks | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
User Story 1: As an Event Enthusiast, Event Organizer sign up using my email, phone number, name, and password, and select my category (Event Enthusiast or Event Organizer) I can create a personalized account and access features that match my role.
Task 1.1: Design signup interface (fields for name, email, phone, password, category). | Rania Farhan | 6 | 5 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
• Task 1.2: Implement signup validation and data saving to database. | Rania Farhan | 5 | 5 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 2: As an Event Enthusiast, Event Organizer, Admin, Support Team log in using my registered email or phone number and password I can securely access my account and use the website according to my role.
Task 2.1: Design login page (email/phone, password, forgot password) | Rania Farhan | 5 | 4 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.2: Connect login page to authentication system (role-based access). | Rania Farhan | 6 | 5 | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 3: As an event enthusiast I want to browse and search for events by category, date, or location so that I can easily find events that match my interests.
Task 3.1 Design the event browsing interface (filters by category/date/location). | Rania Farhan | 7 | 7 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 3.2 Connect browsing feature to the event database | Rania Farhan | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
User Story 4: As an Event Organizer I want to create and publish my events on the website so that I can reach more people and promote my event.
Task 4.1: Design “Create Event” form UI (title, date, description, image, capacity) | Shahad Alotaibi | 7 | 5 | 2 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 4.2: Implement backend logic for event creation and saving to database | Shahad Alotaibi | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 4.3: Enable event publishing & admin approval workflow | Shahad Alotaibi | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 5: As a Event Enthusiast l want to Book event tickets online so that I can save time and avoid waiting in lines.
Task 5.1 Design ticket booking UI with event details and seat options | Rania Farhan | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Task 5.2 Send confirmation email or message after successful booking | Layan Ahmad | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0
User Story 6: As a Admin I want to Review and approve events created by organizers so that I can verified and appropriate events are published on the website.
Task 6.1: Design “Admin Event Review” interface showing event details (title, description, organizer info, date). | Lamyaa Alotaibi | 6 | 5 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 6.2: Implement backend logic to fetch pending events from the database for admin review. | Lamyaa Alotaibi | 7 | 6 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 6.3: Implement “Approve” and “Reject” functionality with status update in database. | Lamyaa Alotaibi | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 6.4: send an alert after approval/rejection. | Layan Ahmad | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task 6.5: Test event approval workflow to ensure only verified events are published. | Lamyaa Alotaibi | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
User Story 7: As an Admin, I want to View all support issues so that I can monitor user problems and ensure they are handled properly.
Task 7.1: Create an admin page that displays all support issues. | Layan Ahmad | 3 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 7.2: Fetch issues from the database and list them in a table. | Shahad Alotaibi | 6 | 5 | 1 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 7.3: Add role validation so only Admin and support can access the page. | Shahad Alotaibi | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 7.4: Sort issues by newest first. | Shahad Alotaibi | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
User Story 8: As a Support, I want to View all user issues and update their status so that I can manage and resolve user complaints efficiently.
Task 8.1: Create backend query to fetch all issues assigned to the support dashboard. | Shahad Alotaibi | 6 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 8.2: Display issues in a table with columns (ID, User, Subject, Status, Priority, Created). | Shahad Alotaibi | 4 | 3 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 8.3: Add a dropdown for updating issue status. | Shahad Alotaibi | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 8.4: Implement POST request to update the issue’s status in the database. | Shahad Alotaibi | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 9: As an Event Enthusiast I want to view, download, and manage my booked tickets so that I can easily access them during events or share them if needed.
Task 9.1: Design “My Tickets” page UI (list of booked events, ticket details, and options). | Lamyaa Alotaibi | 5 | 4 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 9.2: Implement backend logic to fetch user’s booked tickets from the database. | Rania Farhan | 7 | 6 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 9.3: Add “Download Ticket (PDF) ” and "View Ticket ( QR Code)" functionality. | Lamyaa Alotaibi | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 9.4:Implement “Cancel Ticket” and “Share Ticket” options for user management. | Rania Farhan | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
Task 9.5: Test ticket management features (view/download/share/cancel). | Lamyaa Alotaibi | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0
User Story 10: As an Event Enthusiast, I want to receive email and SMS notifications for any updates to my booked events so that I stay informed about any schedule changes or details.
Task 10.1: Add notification feature (email and SMS) for event updates. | Shahad Alotaibi | 6 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 10.2: Send automatic message when event date or time changes. | Shahad Alotaibi | 5 | 3 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 11: As a Event Enthusiast l want to Discover different events based on my interests so that I can attend events that match what I enjoy.
Task 11.1 Develop search and filter functions by category and location | Layan Ahmad | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 11.2 Implement recommendation system based on user preferences | Layan Ahmad | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0
User Story 12: As an Admin, I want to manage users, via Dashboard and event data so that I can ensure the system is running smoothly and securely.
Task 12.1 Design admin dashboard for managing users, permissions, and event data. | Raghad Alsemaih | 6 | 6 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 12.2 Test and maintain admin functions. | Raghad Alsemaih | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
Task 12.3 Monitor data consistency and accuracy. | Raghad Alsemaih | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
User Story 13: As an Event Organizer, I want to manage attendees and view booking analytics so that I can monitor event performance and attendance trends.
Task 13.1: Design attendee management interface (view, edit, remove attendee details) | Layan Ahmad | 5 | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 13.2 Implement backend logic for attendee data & syncing with event database | Layan Ahmad | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task 13.3 Develop analytics dashboard for attendance trends & booking stats | Layan Ahmad | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 205 | 55 | 8

## Phase 3
14-DAY SPRINT BACKLOG
2025-11-02 | 2025-11-20 | 29 |  | 27 |  | 2
SPRINT GOAL | Deliver core event management functionalities including user registration, event browsing, event creation, event booking, event approval, and issue tracking.
SPRINT TRACKING |  |  |  |  | 2025-11-02
User Stories and Tasks | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
User story 1.1: As an Event Organizer, I want to edit my events so I can update event details. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1.1 add “Edit Event” button in the organizer events page. | Rania | 5 | 5 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1.2 Create “Edit Event” form to update event details (name, description, date, time, price, capacity, category, venue). | Rania | 6 | 4 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.1.3 Develop backend logic to update the event in the database. | Raghad | 5 | 5 | 0 | 2025-11-02 DAY 5: 2; 2025-11-02 DAY 6: 3
User story 1.2 As an Event Organizer, I want to delete my events so I stop registrations when needed. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 1.2.1 Add “Delete Event” button to allow organizer to remove an event. | Rania | 4 | 4 | 0 | 2025-11-02 DAY 7: 2; 2025-11-02 DAY 8: 2
Task 1.2.2 Implement confirmation prompt before deleting an event. | Rania | 1 | 1 | 0 | bar: 2025-11-02 DAY 9
Task 1.2.3: Develop backend logic to delete event safely without breaking bookings/tickets. | Raghad | 4 | 4 | 0 | 2025-11-02 DAY 10: 2; 2025-11-02 DAY 11: 2
User Story 2 As a Marketing Team I want to Manage marketing campaigns and ads so that I can increase visibility and engagement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.1: Add Instagram section to homepage UI | Shahad | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.2: Insert clickable Instagram link with brand style | Layan | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2.3: Ensure Instagram link opens externally and works on all devices | Layan | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 3 Event Enthusiast, Event Organizer, Admin, Support Team I want to reset my forgotten password so that I can regain access to my account securely
Task 3.1: Design “Forgot Password” form with email input. | Layan | 5 | 5 | 0 | 2025-11-02 DAY 1: 2; 2025-11-02 DAY 2: 3
Task 3.2: Implement backend logic to generate a secure reset token and store it in the database. | Lamyaa | 4 | 3 | 1 | 2025-11-02 DAY 3: 2; 2025-11-02 DAY 4: 1
Task 3.3: Create “Reset Password” page to enter a new password using the token. | Layan | 4 | 2 | 2 | 2025-11-02 DAY 7: 2
Task 3.4: Validate token, update password in database, and show success confirmation. | Shahad | 4 | 4 | 0 | 2025-11-02 DAY 8: 2; 2025-11-02 DAY 9: 2
TOTAL |  | 29 | 27 | 2