## BURNDOWN CHART
BURNDOWN CHART
Days | Goal | Done | Goal velocity | Remaining
0 | 0 | 0 | 96 | 96
1 | 10 | 10 | 86 | 86
2 | 10 | 10 | 76 | 76
3 | 10 | 8 | 66 | 68
4 | 10 | 10 | 56 | 58
5 | 10 | 14 | 46 | 44
6 | 10 | 8 | 36 | 36
7 | 10 | 7 | 26 | 29
8 | 10 | 10 | 16 | 19
9 | 10 | 13 | 6 | 6
10 | 6 | 6 | 0 | 0
96 Story Points
In 2 weeks (5 days for each)
96/10 =9.6 = 10
Note on B8: stakeholdermap.com: Change the timescale to suit you needs e.g. Sprint or Iteration.
Note on C8: stakeholdermap.com: Number of features or story points you plan to complete.
Note on F8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## PROJECT DETAILS
PROJECT NUMBER | 3
PROJECT NAME | Event Hub
PROJECT MANAGER
DATE | 2025-11-01
VERSION | V1.1

## INSTRUCTIONS
Instructions
Days
Change this to the timescale that you want to appear at the bottom of the chart (the x axis).
Goal or target
Enter the number of features/story points that you plan to achieve in each time period. This forms the yellow line showing goal velocity on the chart.
Done or actual
Record how many features/story points that you actually achieve.
Goal or target velocity
This is a calculated field that counts down the target points to zero (completion of the project). It forms the left side of the chart (the y axis).
Remaining
This is a calculated field that simply deducts Done from Remaining. It is the blue line showing the actual burndown rate on the chart.